## MeetingRecord
Date | Method | Attendees |  |  |  | Purpose | Time
2020-01-14 | IRL | JH | ALH | AJH | JWM | Task Navigation/ Allocation | 2 | Key
2020-01-21 | IRL |  | ALH | AJH | JWM | Task Navigation/ Allocation | 2
2020-01-28 | IRL | JH | ALH | AJH | JWM | Code Implementation | 2 | Group Member Name | Group Members Initials
2020-01-29 | IRL |  | ALH | AJH | JWM | Progress Discussion | 3 | Joseph Hill | JH
2020-02-04 | IRL |  | ALH | AJH | JWM | Code Implementation | 2 | Adam Leonard Hubble | ALH
2020-02-11 | IRL |  | ALH | AJH | JWM | Code Implementation | 2 | Alfie John Horton | AJH
2020-02-18 | IRL |  | ALH | AJH | JWM | Code Implementation | 2 | Jack Wilson Moorin | JWM
Sunday, March 1, 2020 | IRL |  | ALH | AJH | JWM | Progress Discussion | 2
Tuesday, March 3, 2020 | IRL |  | ALH | AJH | JWM | Code Implementation | 2
Wednesday, March 4, 2020 | IRL |  | ALH | AJH | JWM | Code Implementation | 0.5 | Methods
Friday, March 6, 2020 | IRL |  | ALH | AJH | JWM | Progress Discussion | 0.5
2020-03-10 | IRL |  | ALH | AJH | JWM | Code Implementation | 2 | IRL
2020-03-17 | IRL |  | ALH | AJH | JWM | Code Implementation | 2 | Video
Tuesday, March 17, 2020 | IRL |  | ALH | AJH | JWM | Code Implementation | 3 | Audio
2020-03-24 | IRL |  | ALH | AJH | JWM | Progress Discussion | 2
2020-03-31 | IRL |  | ALH | AJH | JWM | Code Implementation | 2
2020-04-07 | IRL |  | ALH | AJH | JWM | Progress Discussion | 3 | Purposes
2020-04-14 | IRL |  | ALH | AJH | JWM | Task Navigation/ Allocation | 2
2020-04-21 | IRL |  | ALH | AJH | JWM | Progress Discussion | 2 | Task Navigation/ Allocation
2020-04-28 | IRL |  | ALH | AJH | JWM | Progress Discussion | 2 | Code Implementation
2020-05-04 | IRL |  | ALH | AJH |  | Code Implementation | 5 | Progress Discussion
2020-05-11 | IRL |  | ALH | AJH | JWM | Progress Discussion | 2
2020-05-12 | IRL |  | ALH | AJH | JWM | Code Implementation | 2
2020-05-19 | IRL |  | ALH | AJH | JWM | Task Navigation/ Allocation | 2 | Time Spent
2020-05-26 | IRL |  | ALH | AJH | JWM | Progress Discussion | 2
2020-06-02 | IRL |  | ALH | AJH | JWM | Code Implementation | 2 | 77
2020-06-09 | IRL |  | ALH | AJH | JWM | Progress Discussion | 2
2020-06-16 | IRL |  | ALH | AJH | JWM | Task Navigation/ Allocation | 2
2020-06-23 | IRL |  | ALH | AJH | JWM | Progress Discussion | 2
2020-06-30 | IRL |  | ALH | AJH | JWM | Progress Discussion | 2
2020-07-07 | IRL |  | ALH | AJH | JWM | Task Navigation/ Allocation | 2
2020-07-14 | IRL |  | ALH | AJH | JWM | Progress Discussion | 2
2020-07-21 | IRL |  | ALH | AJH | JWM | Progress Discussion | 2
2020-07-28 | IRL |  | ALH | AJH | JWM | Progress Discussion | 2
2020-07-04 | IRL |  | ALH | AJH | JWM | Progress Discussion | 2
2020-07-11 | IRL |  | ALH | AJH | JWM | Progress Discussion | 4

## Timesheet
Group Member | Time Spent (hours) | Date | Activity | Key
JH | 0 | 2020-01-21 | ASSIMP loader
ALH | 2 | 2020-01-21 | Administration | Group Member Name | Group Members Initials
AJH | 2 | 2020-01-21 | Helping (ASSIMP) | Joseph Hill | JH
JWM | 2 | 2020-01-21 | IMGui | Adam Leonard Hubble | ALH
ALH | 4 | 2020-01-21 | Administration | Alfie John Horton | AJH
AJH | 4.5 | 2020-01-26 | Physics | Jack Wilson Moorin | JWM
ALH | 2 | 2020-01-27 | IMGui
AJH | 2 | 2020-01-27 | IMGui
JWM | 1 | 2020-01-27 | IMGui | Individual Time Investment
ALH | 2 | 2020-01-28 | Administration
AJH | 2 | 2020-01-28 | Helping (IMGui) | Group Member Name | Time Accumulated (hours)
JWM | 2 | 2020-01-28 | IMGui | Joseph Hill | 4
JH | 2 | 2020-01-28 | ASSIMP loader | Adam Leonard Hubble | 210.5
AJH | 4.5 | 2020-01-28 | Physics | Alfie John Horton | 280
AJH | 1.5 | 2020-01-29 | Helping (ASSIMP) | Jack Wilson Moorin | 155.5
ALH | 1.5 | 2020-01-29 | Helping (ASSIMP)
JWM | 2.5 | 2020-01-29 | IMGui
AJH | 4 | 2020-01-30 | Physics | Collective Time Investment
ALH | 6 | 2020-01-30 | Profiler
AJH | 6 | 2020-01-31 | Level Editor | Total Time (hours) | 650
ALH | 2 | 2020-01-31 | Profiler
AJH | 7 | 2020-02-01 | Level Editor
AJH | 6.5 | 2020-02-02 | Level Editor
ALH | 2 | 2020-02-02 | Profiler
ALH | 5 | 2020-02-03 | Profiler
JWM | 2 | 2020-02-04 | IMGui
ALH | 4 | 2020-02-04 | Administration
AJH | 3 | 2020-02-04 | Physics
JH | 2 | 2020-02-04 | ASSIMP loader
JWM | 3 | 2020-02-05 | IMGui Layout
ALH | 1 | 2020-02-05 | Profiler
AJH | 7 | 2020-02-05 | Level Editor
JWM | 2 | 2020-02-06 | IMGui Layout
AJH | 6 | 2020-02-06 | Level Editor
ALH | 2 | 2020-02-06 | Profiler
ALH | 8 | 2020-02-07 | Processes
AJH | 5 | 2020-02-08 | Level Editor
ALH | 1 | 2020-02-08 | Processes
AJH | 7.5 | 2020-02-09 | Level Editor
ALH | 3 | 2020-02-09 | Processes
AJH | 2 | 2020-02-10 | Level Editor
ALH | 2 | 2020-02-10 | Processes
ALH | 7 | 2020-02-11 | Processes
AJH | 4 | 2020-02-11 | Level Editor
AJH | 5 | 2020-02-12 | Level Editor
ALH | 6 | 2020-02-12 | Processes
ALH | 1 | 2020-02-12 | Frame Buffers
AJH | 2 | 2020-02-13 | Level Editor
ALH | 4 | 2020-02-13 | Frame Buffers
ALH | 4 | 2020-02-14 | Frame Buffers
AJH | 3 | 2020-02-15 | Level Editor
AJH | 5 | 2020-02-16 | Level Editor
JWM | 4 | 2020-02-16 | Lua Scripting Set Up
ALH | 5 | 2020-02-17 | Frame Buffers
AJH | 2 | 2020-02-17 | Helping (Frame Buffers)
ALH | 2 | 2020-02-18 | Frame Buffers
JWM | 2 | 2020-02-18 | Lua Scripting Set Up
JWM | 2 | 2020-02-18 | Lua Scripting Set Up
JWM | 1 | 2020-02-19 | Lua Scripting Set Up
AJH | 5 | 2020-02-20 | Level Editor
JWM | 3 | 2020-02-21 | Level Editor GUI
AJH | 7 | 2020-02-21 | ASSIMP loader
AJH | 8 | 2020-02-22 | Level Editor
AJH | 7 | 2020-02-23 | Level Editor
AJH | 1 | 2020-02-24 | Level Editor
AJH | 6 | 2020-02-25 | Textures/ Normal Mapping
AJH | 1.5 | 2020-02-26 | Textures
AJH | 8 | 2020-02-28 | Textures/ Parallax Mapping/ Cube Maps
ALH | 1 | 2020-02-29 | Frame Buffers
AJH | 2 | 2020-03-01 | Frame Buffers
AJH | 2 | 2020-03-02 | Lighting
JWM | 2 | 2020-03-03 | Lua Scripting
AJH | 2 | 2020-03-03 | Frame Buffers
ALH | 2 | 2020-03-03 | Frame Buffers
JWM | 2 | 2020-03-03 | Lua Scripting
AJH | 7 | 2020-03-06 | Physics
JWM | 4 | 2020-03-06 | Lua Scripting
ALH | 5 | 2020-03-10 | Frame Buffers
JWM | 3 | 2020-03-10 | Lua Scripting
AJH | 5 | 2020-03-10 | Physics
AJH | 1 | 2020-03-11 | Level Editor
ALH | 2 | 2020-03-17 | Frame Buffers
AJH | 3.5 | 2020-03-17 | Level Editor
JWM | 2 | 2020-03-17 | Lua Scripting
ALH | 3 | 2020-03-17 | Lua Scripting Help
AJH | 3 | 2020-03-17 | Lua Scripting Help
JWM | 4 | 2020-03-17 | Lua Scripting
JWM | 5 | 2020-03-18 | Lua Scripting
AJH | 2 | 2020-03-18 | Level Editor
AJH | 7 | 2020-03-19 | Level Editor
AJH | 6.5 | 2020-03-20 | Level Editor
AJH | 2.5 | 2020-03-26 | Level Editor
JWM | 5 | 2020-03-31 | Lua Scripting Help Button and Game
AJH | 2.5 | 2020-04-14 | Level Editor
AJH | 2 | 2020-04-16 | Physics
AJH | 4.5 | 2020-04-17 | Physics/ Level Editor
AJH | 6 | 2020-04-19 | Physics Multithreading
AJH | 6 | 2020-04-20 | Multithreading
ALH | 5 | 2020-05-04 | Frame Buffers
AJH | 5 | 2020-05-04 | Frame Buffers
AJH | 6 | 2020-05-05 | Multithreading
AJH | 5 | 2020-05-06 | Multithreading/ Frame Buffers
ALH | 9 | 2020-05-06 | Frame Buffers
JWM | 7 | 2020-05-06 | Lua Scripting
ALH | 12 | 2020-05-07 | FrameBuffers
JWM | 6 | 2020-05-07 | Lua Scripting
ALH | 10 | 2020-05-08 | Frame Buffers
JWM | 8 | 2020-05-08 | Lua Scripting
ALH | 12 | 2020-05-09 | Frame Buffers
AJH | 3 | 2020-05-10 | Multithreading/Level Editor
ALH | 11 | 2020-05-10 | Frame Buffers
AJH | 5 | 2020-05-11 | Multithreading
ALH | 12 | 2020-05-11 | Frame Buffers
JWM | 7 | 2020-05-11 | Lua Scripting
ALH | 8 | 2020-05-12 | Frame Buffers
JWM | 7 | 2020-05-12 | Lua Scripting
ALH | 10 | 2020-05-13 | Frame Buffers
JWM | 6 | 2020-05-13 | Lua Scripting
AJH | 5 | 2020-05-15 | Physics
ALH | 8 | 2020-05-15 | Frame Buffers
AJH | 3 | 2020-05-16 | Physics
JWM | 2 | 2020-05-16 | Lua Scripting
ALH | 4 | 2020-05-16 | Frame Buffers
ALH | 4 | 2020-05-17 | Frame Buffers (Shadow)
ALH | 1 | 2020-05-18 | Frame Buffers (Shadow)
ALH | 6 | 2020-05-20 | Frame Buffers (Shadow)
AJH | 5 | 2020-05-20 | Helping (Frame Buffers (Shadow))
AJH | 6 | 2020-05-21 | Level Editor/Frame Buffers (Shadow)
ALH | 6 | 2020-05-21 | Frame Buffers (Shadow)
AJH | 4 | 2020-05-22 | Frame Buffers (Shadow)
ALH | 3 | 2020-05-22 | Frame Buffers (Shadow)
AJH | 4 | 2020-05-23 | Level Editor
AJH | 5 | 2020-05-24 | Level Editor
AJH | 4 | 2020-05-25 | Level Editor
AJH | 5 | 2020-05-26 | Level Editor
AJH | 5 | 2020-05-27 | Level Editor
AJH | 1 | 2020-05-28 | Level Editor
JWM | 4 | 2020-06-01 | Lua Help Text
AJH | 1.5 | 2020-06-08 | Physics
JWM | 5 | 2020-06-10 | Lua Script Add Object Function
JWM | 8 | 2020-06-11 | Lua Script Add Object Function
JWM | 4 | 2020-06-12 | Lua Script Prefabs for Object Creation
AJH | 3 | 2020-06-14 | Level Editor
JWM | 5.5 | 2020-06-28 | Lua Help Text
JWM | 5.5 | 2020-06-29 | Lua Help Text (Vectors and Colour)
JWM | 5 | 2020-07-01 | Lua Script Prefabs Help Text
JWM | 5 | 2020-07-02 | Lua Script Prefabs
JWM | 4 | 2020-07-04 | Lua Script Prefabs
JWM | 4 | 2020-07-06 | Lua Script Prefabs
JWM | 5 | 2020-07-08 | Lua Script Prefabs Colliders
JWM | 4 | 2020-07-09 | Lua Script Prefabs Lua Scripts
AJH | 5 | 2020-08-10 | Level Editor

## Burndown Chart
Day | Date | Invested Total Hours | Remaining Total Hours | Target Total Hours
1 | 2020-01-14 | 0 | 650 | 646.9626
2 | 2020-01-15 | 0 | 650 | 643.9252
3 | 2020-01-16 | 0 | 650 | 640.8879
4 | 2020-01-17 | 0 | 650 | 637.8505
5 | 2020-01-18 | 0 | 650 | 634.8131
6 | 2020-01-19 | 0 | 650 | 631.7757
7 | 2020-01-20 | 0 | 650 | 628.7383
8 | 2020-01-21 | 10 | 640 | 625.7009
9 | 2020-01-22 | 0 | 640 | 622.6636
10 | 2020-01-23 | 0 | 640 | 619.6262
11 | 2020-01-24 | 0 | 640 | 616.5888
12 | 2020-01-25 | 0 | 640 | 613.5514
13 | 2020-01-26 | 4.5 | 635.5 | 610.514
14 | 2020-01-27 | 5 | 630.5 | 607.4766
15 | 2020-01-28 | 12.5 | 618 | 604.4393
16 | 2020-01-29 | 5.5 | 612.5 | 601.4019
17 | 2020-01-30 | 10 | 602.5 | 598.3645
18 | 2020-01-31 | 8 | 594.5 | 595.3271
19 | 2020-02-01 | 7 | 587.5 | 592.2897
20 | 2020-02-02 | 8.5 | 579 | 589.2523
21 | 2020-02-03 | 5 | 574 | 586.215
22 | 2020-02-04 | 11 | 563 | 583.1776
23 | 2020-02-05 | 11 | 552 | 580.1402
24 | 2020-02-06 | 10 | 542 | 577.1028
25 | 2020-02-07 | 8 | 534 | 574.0654
26 | 2020-02-08 | 6 | 528 | 571.028
27 | 2020-02-09 | 10.5 | 517.5 | 567.9907
28 | 2020-02-10 | 4 | 513.5 | 564.9533
29 | 2020-02-11 | 11 | 502.5 | 561.9159
30 | 2020-02-12 | 12 | 490.5 | 558.8785
31 | 2020-02-13 | 6 | 484.5 | 555.8411
32 | 2020-02-14 | 4 | 480.5 | 552.8037
33 | 2020-02-15 | 3 | 477.5 | 549.7664
34 | 2020-02-16 | 9 | 468.5 | 546.729
35 | 2020-02-17 | 7 | 461.5 | 543.6916
36 | 2020-02-18 | 6 | 455.5 | 540.6542
37 | 2020-02-19 | 1 | 454.5 | 537.6168
38 | 2020-02-20 | 5 | 449.5 | 534.5794
39 | 2020-02-21 | 10 | 439.5 | 531.5421
40 | 2020-02-22 | 8 | 431.5 | 528.5047
41 | 2020-02-23 | 7 | 424.5 | 525.4673
42 | 2020-02-24 | 1 | 423.5 | 522.4299
43 | 2020-02-25 | 6 | 417.5 | 519.3925
44 | 2020-02-26 | 1.5 | 416 | 516.3551
45 | 2020-02-27 | 0 | 416 | 513.3178
46 | 2020-02-28 | 8 | 408 | 510.2804
47 | 2020-02-29 | 1 | 407 | 507.243
48 | 2020-03-01 | 2 | 405 | 504.2056
49 | 2020-03-02 | 2 | 403 | 501.1682
50 | 2020-03-03 | 8 | 395 | 498.1308
51 | 2020-03-04 | 0 | 395 | 495.0935
52 | 2020-03-05 | 0 | 395 | 492.0561
53 | 2020-03-06 | 11 | 384 | 489.0187
54 | 2020-03-07 | 0 | 384 | 485.9813
55 | 2020-03-08 | 0 | 384 | 482.9439
56 | 2020-03-09 | 0 | 384 | 479.9065
57 | 2020-03-10 | 13 | 371 | 476.8692
58 | 2020-03-11 | 1 | 370 | 473.8318
59 | 2020-03-12 | 0 | 370 | 470.7944
60 | 2020-03-13 | 0 | 370 | 467.757
61 | 2020-03-14 | 0 | 370 | 464.7196
62 | 2020-03-15 | 0 | 370 | 461.6822
63 | 2020-03-16 | 0 | 370 | 458.6449
64 | 2020-03-17 | 17.5 | 352.5 | 455.6075
65 | 2020-03-18 | 7 | 345.5 | 452.5701
66 | 2020-03-19 | 7 | 338.5 | 449.5327
67 | 2020-03-20 | 6.5 | 332 | 446.4953
68 | 2020-03-21 | 0 | 332 | 443.4579
69 | 2020-03-22 | 0 | 332 | 440.4206
70 | 2020-03-23 | 0 | 332 | 437.3832
71 | 2020-03-24 | 0 | 332 | 434.3458
72 | 2020-03-25 | 0 | 332 | 431.3084
73 | 2020-03-26 | 2.5 | 329.5 | 428.271
74 | 2020-03-27 | 0 | 329.5 | 425.2336
75 | 2020-03-28 | 0 | 329.5 | 422.1963
76 | 2020-03-29 | 0 | 329.5 | 419.1589
77 | 2020-03-30 | 0 | 329.5 | 416.1215
78 | 2020-03-31 | 5 | 324.5 | 413.0841
79 | 2020-04-01 | 0 | 324.5 | 410.0467
80 | 2020-04-02 | 0 | 324.5 | 407.0093
81 | 2020-04-03 | 0 | 324.5 | 403.972
82 | 2020-04-04 | 0 | 324.5 | 400.9346
83 | 2020-04-05 | 0 | 324.5 | 397.8972
84 | 2020-04-06 | 0 | 324.5 | 394.8598
85 | 2020-04-07 | 0 | 324.5 | 391.8224
86 | 2020-04-08 | 0 | 324.5 | 388.785
87 | 2020-04-09 | 0 | 324.5 | 385.7477
88 | 2020-04-10 | 0 | 324.5 | 382.7103
89 | 2020-04-11 | 0 | 324.5 | 379.6729
90 | 2020-04-12 | 0 | 324.5 | 376.6355
91 | 2020-04-13 | 0 | 324.5 | 373.5981
92 | 2020-04-14 | 2.5 | 322 | 370.5607
93 | 2020-04-15 | 0 | 322 | 367.5234
94 | 2020-04-16 | 2 | 320 | 364.486
95 | 2020-04-17 | 4.5 | 315.5 | 361.4486
96 | 2020-04-18 | 0 | 315.5 | 358.4112
97 | 2020-04-19 | 6 | 309.5 | 355.3738
98 | 2020-04-20 | 6 | 303.5 | 352.3364
99 | 2020-04-21 | 0 | 303.5 | 349.2991
100 | 2020-04-22 | 0 | 303.5 | 346.2617
101 | 2020-04-23 | 0 | 303.5 | 343.2243
102 | 2020-04-24 | 0 | 303.5 | 340.1869
103 | 2020-04-25 | 0 | 303.5 | 337.1495
104 | 2020-04-26 | 0 | 303.5 | 334.1121
105 | 2020-04-27 | 0 | 303.5 | 331.0748
106 | 2020-04-28 | 0 | 303.5 | 328.0374
107 | 2020-04-29 | 0 | 303.5 | 325
108 | 2020-04-30 | 0 | 303.5 | 321.9626
109 | 2020-05-01 | 0 | 303.5 | 318.9252
110 | 2020-05-02 | 0 | 303.5 | 315.8879
111 | 2020-05-03 | 0 | 303.5 | 312.8505
112 | 2020-05-04 | 10 | 293.5 | 309.8131
113 | 2020-05-05 | 6 | 287.5 | 306.7757
114 | 2020-05-06 | 21 | 266.5 | 303.7383
115 | 2020-05-07 | 18 | 248.5 | 300.7009
116 | 2020-05-08 | 18 | 230.5 | 297.6636
117 | 2020-05-09 | 12 | 218.5 | 294.6262
118 | 2020-05-10 | 14 | 204.5 | 291.5888
119 | 2020-05-11 | 24 | 180.5 | 288.5514
120 | 2020-05-12 | 15 | 165.5 | 285.514
121 | 2020-05-13 | 16 | 149.5 | 282.4766
122 | 2020-05-14 | 0 | 149.5 | 279.4393
123 | 2020-05-15 | 13 | 136.5 | 276.4019
124 | 2020-05-16 | 9 | 127.5 | 273.3645
125 | 2020-05-17 | 4 | 123.5 | 270.3271
126 | 2020-05-18 | 1 | 122.5 | 267.2897
127 | 2020-05-19 | 0 | 122.5 | 264.2523
128 | 2020-05-20 | 11 | 111.5 | 261.215
129 | 2020-05-21 | 12 | 99.5 | 258.1776
130 | 2020-05-22 | 7 | 92.5 | 255.1402
131 | 2020-05-23 | 4 | 88.5 | 252.1028
132 | 2020-05-24 | 5 | 83.5 | 249.0654
133 | 2020-05-25 | 4 | 79.5 | 246.028
134 | 2020-05-26 | 5 | 74.5 | 242.9907
135 | 2020-05-27 | 5 | 69.5 | 239.9533
136 | 2020-05-28 | 1 | 68.5 | 236.9159
137 | 2020-05-29 | 0 | 68.5 | 233.8785
138 | 2020-05-30 | 0 | 68.5 | 230.8411
139 | 2020-05-31 | 0 | 68.5 | 227.8037
140 | 2020-06-01 | 4 | 64.5 | 224.7664
141 | 2020-06-02 | 0 | 64.5 | 221.729
142 | 2020-06-03 | 0 | 64.5 | 218.6916
143 | 2020-06-04 | 0 | 64.5 | 215.6542
144 | 2020-06-05 | 0 | 64.5 | 212.6168
145 | 2020-06-06 | 0 | 64.5 | 209.5794
146 | 2020-06-07 | 0 | 64.5 | 206.5421
147 | 2020-06-08 | 1.5 | 63 | 203.5047
148 | 2020-06-09 | 0 | 63 | 200.4673
149 | 2020-06-10 | 5 | 58 | 197.4299
150 | 2020-06-11 | 8 | 50 | 194.3925
151 | 2020-06-12 | 4 | 46 | 191.3551
152 | 2020-06-13 | 0 | 46 | 188.3178
153 | 2020-06-14 | 3 | 43 | 185.2804
154 | 2020-06-15 | 0 | 43 | 182.243
155 | 2020-06-16 | 0 | 43 | 179.2056
156 | 2020-06-17 | 0 | 43 | 176.1682
157 | 2020-06-18 | 0 | 43 | 173.1308
158 | 2020-06-19 | 0 | 43 | 170.0935
159 | 2020-06-20 | 0 | 43 | 167.0561
160 | 2020-06-21 | 0 | 43 | 164.0187
161 | 2020-06-22 | 0 | 43 | 160.9813
162 | 2020-06-23 | 0 | 43 | 157.9439
163 | 2020-06-24 | 0 | 43 | 154.9065
164 | 2020-06-25 | 0 | 43 | 151.8692
165 | 2020-06-26 | 0 | 43 | 148.8318
166 | 2020-06-27 | 0 | 43 | 145.7944
167 | 2020-06-28 | 5.5 | 37.5 | 142.757
168 | 2020-06-29 | 5.5 | 32 | 139.7196
169 | 2020-06-30 | 0 | 32 | 136.6822
170 | 2020-07-01 | 5 | 27 | 133.6449
171 | 2020-07-02 | 5 | 22 | 130.6075
172 | 2020-07-03 | 0 | 22 | 127.5701
173 | 2020-07-04 | 4 | 18 | 124.5327
174 | 2020-07-05 | 0 | 18 | 121.4953
175 | 2020-07-06 | 4 | 14 | 118.4579
176 | 2020-07-07 | 0 | 14 | 115.4206
177 | 2020-07-08 | 5 | 9 | 112.3832
178 | 2020-07-09 | 4 | 5 | 109.3458
179 | 2020-07-10 | 0 | 5 | 106.3084
180 | 2020-07-11 | 0 | 5 | 103.271
181 | 2020-07-12 | 0 | 5 | 100.2336
182 | 2020-07-13 | 0 | 5 | 97.1963
183 | 2020-07-14 | 0 | 5 | 94.1589
184 | 2020-07-15 | 0 | 5 | 91.1215
185 | 2020-07-16 | 0 | 5 | 88.0841
186 | 2020-07-17 | 0 | 5 | 85.0467
187 | 2020-07-18 | 0 | 5 | 82.0093
188 | 2020-07-19 | 0 | 5 | 78.972
189 | 2020-07-20 | 0 | 5 | 75.9346
190 | 2020-07-21 | 0 | 5 | 72.8972
191 | 2020-07-22 | 0 | 5 | 69.8598
192 | 2020-07-23 | 0 | 5 | 66.8224
193 | 2020-07-24 | 0 | 5 | 63.785
194 | 2020-07-25 | 0 | 5 | 60.7477
195 | 2020-07-26 | 0 | 5 | 57.7103
196 | 2020-07-27 | 0 | 5 | 54.6729
197 | 2020-07-28 | 0 | 5 | 51.6355
198 | 2020-07-29 | 0 | 5 | 48.5981
199 | 2020-07-30 | 0 | 5 | 45.5607
200 | 2020-07-31 | 0 | 5 | 42.5234
201 | 2020-08-01 | 0 | 5 | 39.486
202 | 2020-08-02 | 0 | 5 | 36.4486
203 | 2020-08-03 | 0 | 5 | 33.4112
204 | 2020-08-04 | 0 | 5 | 30.3738
205 | 2020-08-05 | 0 | 5 | 27.3364
206 | 2020-08-06 | 0 | 5 | 24.2991
207 | 2020-08-07 | 0 | 5 | 21.2617
208 | 2020-08-08 | 0 | 5 | 18.2243
209 | 2020-08-09 | 0 | 5 | 15.1869
210 | 2020-08-10 | 5 | 0 | 12.1495
211 | 2020-08-11 | 0 | 0 | 9.1121
212 | 2020-08-12 | 0 | 0 | 6.0748
213 | 2020-08-13 | 0 | 0 | 3.0374
214 | 2020-08-14 | 0 | 0 | 0
Formulas:
Date = [Date, row above]+1

## _56F9DC9755BA473782653E2940F9 (hidden)
48B4T1DS3027HBXTFFaXzOwuPUcU8H1PjJhnDek97URUM1lLNFBUUldIVFNLM0pKV1dZQjdRQkNNRy4u
Form1
{52170e4a-ac43-4780-858d-66f0e212fe7b}

## Kanban Board
To Do | [6 empty] | In Progress | [6 empty] | Done
ID | Name | Description | Acceptance Criteria | Points | Sprint ID | Developer | ID | Name | Description | Acceptance Criteria | Points | Sprint ID | Developer | ID | Name | Description | Acceptance Criteria | Points | Sprint ID | Developer
[7 empty] | 12 | Create audio manager as basis for audio | Create the audio manager class and other necessary classes for audio to be played in the engine | Create the audio manager and add an audio component for objects to play audio | 10 |  | JH | 1 | IMGui Interface | Redesign created IMGui interface | General appearance of IMGui interface imporoved | 5 | 1 | JWM
[14 empty] | 2 | Link ImGui and React Physics libraries | Link libraries in the premake file so they can be accessed from the engine | Add libraries and setup in premake allowing them to be used in the engine | 5 | 1 | AJH
[14 empty] | 3 | Create required physics components to have collision | Create a physics system and components for physics to run in the engine | Create a physics system to control physics, add components to be on objects which give them physics and collision capabilities | 10 | 1 | AJH
[14 empty] | 4 | Add level editor project | Add the level editor project in the premake file for it to run a separate project | Add the project and link libraries in premake | 5 | 1 | AJH
[14 empty] | 5 | Add model loading with ASSIMP | Link ASSIMP and create required classes for it to load models in the engine | Make the engine able to load models using ASSIMP | 12 | 1 | JH + AH
[14 empty] | 6 | Create project management documents | Create documents to manage project | Create excel spreadsheet, which addresses meeting records, time investment, burndown chart, kanban board and sprint backlog | 25 | 1 | ALH
[14 empty] | 7 | Implement performance profiler tool | Interface to show performance of executing system | Create ImGui window displaying FPS, dropped frames and runtime process times | 20 | 1 | ALH
[14 empty] | 8 | Create base Lua Script component | Make a component for the Lua scripts | Develop a new component for the game objects. Must be able to execute functions within a Lua script file | 10 | 2 | JWM
[14 empty] | 9 | Add Timestep to Lua | Add the timestep variable to Lua | Include the timestep between frames as a read-only variable | 5 | 2 | JWM
[14 empty] | 10 | Make level editor able to save, load and run the game | Add a button in the level editor which saves needed information in JSON files to be reloaded | Use JSON files to save and load a project, make button in the editor to run the game being made | 15 | 2 | AJH
[14 empty] | 11 | Add/remove components in the level editor | Add functionality for objects to have components added and removed in the level editor | Use JSON files to save and load a project, make button in the editor to run the game being made | 8 | 2 | AJH
[14 empty] | 13 | Add ability to change how objects look in the level editor | Add material component variables for editing in the level editor | Add sections to change material and texture components | 5 | 2 | AJH
[14 empty] | 14 | Create frame buffer interface class | Create interface for frame buffer objects | Create and integrate frame buffer interface class | 10 | 2 | ALH
[14 empty] | 15 | Implement OpenGL abstractions of frame buffer interface class | Create class for OpenGL frame buffer objects | Create OpenGL API implementation class of the frame buffer interface class | 10 | 2, 3 | ALH
[14 empty] | 16 | Implement Start and Update functions | Implement functionality for a Start and Update function to be used in the attached Lua script | Must call Start function when object created and the Update function every subsequent frame | 8 | 3 | JWM
[14 empty] | 17 | Implement object transforms | Make the attached object's transform availalable within the Lua script | The attached objects position, scale and rotation must be acceesible from within the attached script | 12 | 3 | JWM
[14 empty] | 18 | Add different texture types for objects | Add different texture types to change the look of an object in the engine | Make the ctexture component able to have a diffuse texture, a specular texture, a normal map and a parallax map. Change shader to use these | 10 | 3 | AJH
[14 empty] | 19 | Add joints to the physics | Add joints which are used to connect two physics objects in the engine | Add all joints as components on objects. Make usable in the level editor | 5 | 3 | AJH
[14 empty] | 20 | Collision filtering | Add collision filtering so some physics objects can not interact with others in the engine | Add the ability to choose in the level editor which colliders hit which | 5 | 3 | AJH
[14 empty] | 21 | Implement post-processing renderer interface class | Create interface for the post-processing renderer | Create and integrate post-proccesing render interface class | 10 | 3, 4 | ALH
[14 empty] | 22 | Add keyboard inputs to Lua | Make keyboard key presses available in Lua scripts | Add functionality to Lua scripts so that the user can tell if a key is being pressed | 8 | 4 | JWM
[14 empty] | 23 | Add mouse inputs to Lua | Make mouse key presses available in Lua scripts | Continuing with the keyboard input functionality include mosue button input as well | 5 | 4 | JWM
[14 empty] | 24 | Add object model functionality | Add functionality pertaining to the model component to the Lua scripts | Add the ability to set the model of the game object from an input filepath | 5 | 4 | JWM
[14 empty] | 25 | Add object material functionality | Add functionality pertaining to the material component to the Lua scripts | Link the object's material into Lua. Include the diffuse, specular and shininess | 5 | 4 | JWM
[14 empty] | 26 | Add object texture height scale | Add the texture height scale to the Lua scripts | Add the attached object's texture's height scale into Lua scripts | 3 | 4 | JWM
[14 empty] | 27 | Add rigid body component functionality to the Lua script component | Add functionality pertaining to the rigid body component to the Lua scripts | Add functionality relating the object's rigid body component. Include apply forces, torque and the linear and angular velocity | 10 | 4 | JWM
[14 empty] | 28 | Add light component functionality to the Lua script component | Add functionality pertaining to the light component to the Lua scripts | Add light component functionality. Include ambient colour, point/specular, directional diffuse/specular and attenuation | 5 | 4 | JWM
[14 empty] | 29 | Make Lua Scripts able to be added in the level editor | Make adding Lua script components possible in the level editor | Add functionality to add/remove Lua Script components, add ability to add an existing one or a new one | 5 | 4 | JWM + AJH
[14 empty] | 30 | Implement OpenGL abstractions of post-processing renderer interface class | Create interface for OpenGL post-processing renderer | Create OpenGL API implementation class of the frame buffer interface class | 10 | 4, 5 | ALH
[14 empty] | 31 | Link Engine Logger functionality | Make the engines logger functions available in the level editor | Add the engines logger functions to the Lua component's functionality. Include all functions | 5 | 5 | JWM
[14 empty] | 32 | Create Lua Scripting help window | Add a help button to the Lua component GUI that has a helpful guide to Lua scripts | Add a help button to the Lua Script component menu, that when clicked on opens up a help window that explains how the component works | 7 | 5 | JWM
[14 empty] | 33 | Use multiple 3D layers | Add the ability to use more than one 3D layer in the level editor and control what layer an object is in | Add ability for the user to add new/delete layers in the level editor and change which layers the camera can see | 10 | 5 | AJH
[14 empty] | 34 | Add functionality to set velocities on physics components | Create accessable functions in the rigidbody component for changing these things | Add functions for setting velocities so that they can be used from the Lua Scripts | 5 | 5 | AJH
[14 empty] | 35 | Add Open button to Lua component GUI | Add a button to the Lua script GUI that opens the attached Lua script when clicked on | Add a button to the Lua Script component GUI that when clicked will open the attached Lua script file | 10 | 5 | JWM
[14 empty] | 36 | Integrate frame buffer-related classes into JSONLayer class | Use frame buffers to visualise the game | Implement frame buffer-related class implementations for setup, with the default frame buffer shader | 15 | 5 | ALH
[14 empty] | 37 | Maintain Lua Script help window | Continue to add to Lua scripting help guide | Continue to maintain the Lua Script help window as more functionality is added to the component | 20 | 6, 10, 11, 12 | JWM
[14 empty] | 38 | Improve performance | Make the engine more efficient by using multiple threads | Make physics updates run on a separate thread | 20 | 6, 7 | AJH
[14 empty] | 39 | Frame buffer colour and depth buffer attachment support | Use frame buffer effects that factor distance and colour | Enable frame buffer objects to employ colour and depth attachments | 5 | 6 | ALH
[14 empty] | 40 | Multi-sampled anti-aliasing for frame buffer objects | Sharpen the edges of objects using texture sampling | Blit MSAA data to frame buffer drawn to screen, for sharpening geometry edges. MSAA level is toggleable and supported by window resize | 10 | 6 | ALH
[14 empty] | 41 | Improve loading speeds | Make loading a game more efficient by separating model loading over multiple threads | Multithread model loading so that it happens faster | 15 | 7 | AJH
[14 empty] | 42 | Implement range of frame buffer effects that employ kernel convolution | Make frame buffer effects that are kernal controlled | Create shader source code for edge detection, sharpen and blur effects, integrate shader source code into JSONLayer class | 5 | 7 | ALH
[14 empty] | 43 | Implement range of frame buffer effects that employ animation, toggling and use frame buffer depth attachement | Make frame buffer effects that are animated, its internel effects can be toggled or factor distance | Create shader source code for night vision, shake confuse and chaos, depth and simulated fog effects, integrate shader source code into JSONLayer class | 5 | 7 | ALH
[14 empty] | 44 | Implement range of frame buffer effects that use frame buffer colour attachment | Make frame buffer effects that manipulate the games colour | Create shader source code for inversed colour, grayscale and metallic effects, integrate shader source code into JSONLayer class | 5 | 7 | ALH
[14 empty] | 45 | Implement frame buffer effect cycling | Allow frame buffers effects to be switched | Enable frame buffer effects to be toggled during runtime | 10 | 7 | ALH
[14 empty] | 46 | Improve Lua Component GUI | Make the Lua Component GUI look better | Improve general appearance of Lui component graphical user interface | 5 | 8 | JWM
[14 empty] | 47 | Add an OnCollision function to Lua script component | Make a function used when collisions happen | Function must be called when the attached object first collides with another object | 5 | 8 | JWM
[14 empty] | 48 | Fix obvious level editor problems | Stop the editor from crashing at points, and fix visual errors | Stop crashing when stopping running the game, fix camera view when not running the game | 15 | 8 | AJH
[14 empty] | 49 | Raycasting | Add the ability for raycasting with physics to the engine | Make functionality for raycasting for it to be used from Lua Scripts | 15 | 8, 10 | AJH
[14 empty] | 50 | Implement wireframe mode, applied to frame buffer effects | Make frame buffers support a wireframe mode | Support wireframe mode, showing object primitives used in parallel to frame buffer effects. Integrate into toggle capabilties | 5 | 8 | ALH
[14 empty] | 51 | Link Alfie's raycasting with Lua | Make Alfie's raycasting available in Lua | Use Luabridge to link Alfie's functionality with Lua | 10 | 9, 10 | JWM
[14 empty] | 52 | Add 2d layers and text objects to the level editor | Make it possible for 2D layers to be added in the level editor, allowing text to be added | Make it possible to add text objects to 2D layers in the level editor, as well as font/sizes | 15 | 9 | AJH
[14 empty] | 53 | Implement multi-pass rendering for supporting shadow mapping | Make frame buffer objects support shadows | Create shader source code, and refactor JSONLayer class, as well as frame buffer interface classes for supporting multiple render passes | 20 | 8, 9 | ALH
[14 empty] | 54 | Define a Prefab class | Make a class used for holding information about game objects | Define a Prefab class that will be used to hold the necessary information to create an object during the game's run-time | 12 | 10, 11 | JWM
[14 empty] | 55 | Implement Instantiate functionality | Make a function to create an object from a prefab | Create in C++ and subsequently link to Lua scripts, instantiate functions that will create an object in the game from a prefab at run-time | 14 | 10, 11 | JWM
[14 empty] | 56 | Define a LuaVector class | Make a class in Lua to use for vectors | Create a LuaVector class that can be used as a go-between for vectors in C++ and Lua. Get all other Lua function that use vectors to use this | 13 | 10 | JWM
[14 empty] | 57 | Add vector maths to LuaVector class | Add vector based math to LuaVector class | Add vector maths function to LuaVectors. Include dotproduct, angle between, addition, subtraction and magnitude | 8 | 10 | JWM
[14 empty] | 58 | Define a LuaColour class | Make a class in Lua to use for colours | Make a LuaColour class to use as a go-between for colours within C++ and Lua. Get all other Lua functions that use colours to use this | 10 | 10 | JWM
[14 empty] | 59 | Add Hexadecimal to LuaColour | Add a function for LuaColours that can set the colour from a hexadecimal string | Add the ability to define a colour in a LuaColour object from a hexadecimal string | 10 | 10 | JWM
[14 empty] | 60 | Add default object meshes to Lua | Add the filepaths of default object meshes to the model namespace | Add default object mesh filepaths to Lua as read-only variables, so they can be set as the object model. Add them to possible prefabs too | 5 | 10 | JWM
[14 empty] | 61 | Define RaycastHit class | Create a class to hold the returned information from a raycast hit | Define a RaycastHit class that will be used to store the returned information from a raycast | 7 | 10 | JWM
[14 empty] | 62 | Make the level editor write shaders for objects | Make the level editor write a unique shader for each object when it is running the game | When the game is run, the level editor needs to write shaders specifically for the textures each object has | 15 | 10 | AJH
[14 empty] | 63 | Add coliders to prefab/instantiate functionality in Lua | Add collider to prefab objects | Prefabs must hold information for colliders and instantiate functions must add them to the object | 12 | 12 | JWM
[14 empty] | 64 | Add Lua scripts to prefab/instantiate functionality in Lua | Add Lua scripts to prefab objects | Prefabs must hold filepath to another Lua script and Instanitate functions must add it to the created object | 10 | 12 | JWM
[14 empty] | 65 | Fix issues causing the level editor to go black when running the game too many times/make sure the level editor is as stable as possible | Stop the level editor screen going black when running the game too many times (fix memory management issues) | Stop issues happening when running the game too many times in the level editor, also fix issues happening when changing levels in the level editor | 20 | 14 | AJH
[14 empty] | 66 | Finalise project management deliverables | Complete all the necessary documentation for project management | Ensure formatting is adhered to for interpretation and charts display information accurately | 25 | 14 | AJH + ALH + JWM

## Sprints
Sprint ID | 1 | Period | 2020-01-24 | 2020-02-07 |  |  |  | Sprint ID | 2 | Period | 2020-02-08 | 2020-02-22 |  |  | Sprint ID | 3 | Period | 2020-02-23 | 2020-03-08
Work Item |  |  | Criteria |  |  | Complete? | Developer | Work Item |  |  | Criteria |  | Complete? | Developer | Work Item |  |  | Criteria |  | Complete? | Developer
Work on Level Editor IMGui interface |  |  | Redesign created GUI elements for better overall appearance |  |  | Yes | JWM | Create base Lua Script component |  |  | Develop a new component for the game objects. Must be able to execute functions within a Lua script file |  | Yes | JWM | Implement Start and Update Function in Lua Script Component |  |  | Make the component call the script's Start function when the object is created and the Update function every subsequent frame |  | Yes | JWM
Link ImGui and React Physics libraries |  |  | Add libraries and setup in premake allowing them to be used in the engine |  |  | Yes | AJH | Add Timestep to Lua Component |  |  | Include the timestep between frames as a read-only variable |  | Yes | JWM | Implement Object Transforms within Lua Script Component |  |  | Using the LuaBridge library, link the attached object's transform to the Lua script, so that it can be read and written to |  | Yes | JWM
Create required physics components to have collision |  |  | Create a physics system to control physics, add components to be on objects which give them physics and collision capabilities |  |  | Yes | AJH | Make level editor able to save, load and run the game |  |  | Use JSON files to save and load a project, make button in the editor to run the game being made |  | Yes | AJH
[15 empty] | Add different texture types for objects |  |  | Make the texture component able to have a diffuse texture, a specular texture, a normal map and a parallax map. Change shader to use these |  | Yes | AJH
[8 empty] | Add/remove components in the level editor |  |  | Components can be added and removed from objects in the level editor, test using physics components |  | Yes | AJH
Add level editor project |  |  | Add the project and link libraries in premake |  |  | Yes | AJH
Add model loading with ASSIMP |  |  | Make the engine able to load models using ASSIMP |  |  | No | JH | Add model loading with ASSIMP |  |  | Make the engine able to load models using ASSIMP |  | Yes | JH AJH | Add joints to the physics |  |  | Add all joints as components on objects. Make usable in the level editor |  | No | AJH
Create project management documents |  |  | Create excel spreadsheet, which addresses meeting records, time investment, burndown chart, kanban board and sprint backlog |  |  | Yes | ALH | Create audio manager as basis for audio |  |  | Create the audio manager and add an audio component for objects to play audio |  | No | JH
[15 empty] | Collision filtering |  |  | Add the ability to choose in the level editor which colliders hit which |  | No | AJH
Implement performance profiler tool |  |  | Create ImGui window displaying FPS, dropped frames and runtime process times |  |  | Yes | ALH | Add ability to change how objects look in the level editor |  |  | Add sections to change material and texture components |  | Yes | AJH
[15 empty] | Implement OpenGL abstractions of frame buffer interface class |  |  | Create OpenGL API implementation class of the frame buffer interface class |  | Yes | ALH
[8 empty] | Create frame buffer interface class |  |  | Create and integrate frame buffer interface class |  | Yes | ALH
[15 empty] | Implement post-processing renderer interface class |  |  | Create and integrate post-proccesing render interface class |  | No | ALH
[8 empty] | Implement OpenGL abstractions of frame buffer interface class |  |  | Create OpenGL API implementation class of the frame buffer interface class |  | No | ALH
Sprint ID | 4 | Period | 2020-03-09 |  | 2020-03-23 |  |  | Sprint ID | 5 | Period | 2020-03-24 | 2020-04-07 |  |  | Sprint ID | 6 | Period | 2020-04-08 | 2020-04-22
Work Item |  |  | Criteria |  |  | Complete? | Developer | Work Item |  |  | Criteria |  | Complete? | Developer | Work Item |  |  | Criteria |  | Complete? | Developer
Add keyboard input to Lua scripts |  |  | Add functionality to Lua scripts so that the user can tell if a key is being pressed |  |  | Yes | JWM | Link Engine Logger functionality |  |  | Add the engines logger functions to the Lua component's functionality. Include all functions |  | Yes | JWM | Maintain Lua Script help window |  |  | Continue to maintain the Lua Script help window as more functionality is added to the component |  | Yes | JWM
Add mouse button input to Lua scripts |  |  | Continuing with the keyboard input functionality include mosue button input as well |  |  | Yes | JWM | Create Lua Scripting help window |  |  | Add a help button to the Lua Script component menu, that when clicked on opens up a help window that explains how the component works |  | Yes | JWM
[15 empty] | Add joints to the physics |  |  | Add all joints as components on objects. Make usable in the level editor |  | Yes | AJH
Add object model functionality |  |  | Add the ability to set the model of the game object from an input filepath |  |  | Yes | JWM
[8 empty] | Use multiple 3D layers |  |  | Add ability for the user to add new/delete layers in the level editor and change which layers the camera can see |  | Yes | AJH
[15 empty] | Collision listening |  |  | When a collision happens, make a function be called that can be usde in a Lua Script |  | Yes | AJH
Add object material functionality |  |  | Link the object's material into Lua. Include the diffuse, specular and shininess |  |  | Yes | JWM
[8 empty] | Add functionality to set velocities on physics components |  |  | Add functions for setting velocities so that they can be used from the Lua Scripts |  | Yes | AJH | Improve performance |  |  | Make physics updates run on a separate thread |  | Yes | AJH
Add object texture height scale |  |  | Add the attached object's texture's height scale into Lua scripts |  |  | Yes | JWM
[8 empty] | Add Open button to component GUI |  |  | Add a button to the Lua Script component GUI that when clicked will open the attached Lua script file |  | Yes | JWM | Frame buffer colour and depth buffer attachment support |  |  | Enable frame buffer objects to employ colour and depth attachments |  | Yes | ALH
Add rigid body component functionality to the Lua script component |  |  | Add functionality relating the object's rigid body component. Include apply forces, torque and the linear and angular velocity |  |  | Yes | JWM
[15 empty] | Multi-sampled anti-aliasing for frame buffer objects |  |  | Blit MSAA data to frame buffer drawn to screen, for sharpening geometry edges. MSAA level is toggleable and supported by window resize |  | Yes | ALH
[8 empty] | Implement OpenGL abstractions of post-processing renderer interface class |  |  | Create OpenGL API implementation class of the post-processing renderer interface class |  | Yes | ALH
Add light component functionality to the Lua script component |  |  | Add light component functionality. Include ambient colour, point/specular, directional diffuse/specular and attenuation |  |  | Yes | JWM
[8 empty] | Integrate frame buffer-related classes into JSONLayer class |  |  | Implement frame buffer-related class implementations for setup, with the default frame buffer shader |  | Yes | ALH
Collision filtering |  |  | Add the ability to choose in the level editor which colliders hit which |  |  | Yes | AJH
Make Lua Scripts able to be added in the level editor |  |  | Add functionality to add/remove Lua Script components, add ability to add an existing one or a new one |  |  | Yes | JWM + AJH
Implement post-processing renderer interface class |  |  | Create and integrate post-proccesing render interface class |  |  | Yes | ALH
Implement OpenGL abstractions of post-processing renderer interface class |  |  | Create OpenGL API implementation class of the post-processing renderer interface class |  |  | No | ALH
Sprint ID | 7 | Period | 2020-04-23 |  | 2020-05-07 |  |  | Sprint ID | 8 | Period | 2020-05-08 | 2020-05-22 |  |  | Sprint ID | 9 | Period | 2020-05-23 | 2020-06-06
Work Item |  |  | Criteria |  |  | Complete? | Developer | Work Item |  |  | Criteria |  | Complete? | Developer | Work Item |  |  | Criteria |  | Complete? | Developer
Improve loading speeds |  |  | Multithread model loading so that it happens faster |  |  | Yes | AJH | Improve Lua Component GUI |  |  | Improve general appearance of Lui component graphical user interface |  | Yes | JWM | Link Alfie's raycasting with Lua |  |  | Use Luabridge to link Alfie's functionality with Lua |  | No | JWM
Improve performance |  |  | Spread object updates over separate threads |  |  | Yes | AJH | Add an OnCollision function to Lua script component |  |  | Function must be called when the attached object first collides with another object |  | Yes | JWM | Add 2d layers and text objects to the level editor |  |  | Make it possible to add text objects to 2D layers in the level editor, as well as font/sizes |  | Yes | AJH
Implement range of frame buffer effects that employ kernel convolution |  |  | Create shader source code for edge detection, sharpen and blur effects, integrate shader source code into JSONLayer class |  |  | Yes | ALH | Maintain Lua Script help window |  |  | Continue to add to and maintain the Lua Script help window as more functionality is added to the component |  | Yes | JWM | Implement multi-pass rendering for supporting shadow mapping |  |  | Create shader source code, and refactor JSONLayer class, as well as frame buffer interface classes for supporting multiple render passes |  | Yes | ALH + AJH
Implement range of frame buffer effects that employ animation, toggling and use frame buffer depth attachement |  |  | Create shader source code for night vision, shake confuse and chaos, depth and simulated fog effects, integrate shader source code into JSONLayer class |  |  | Yes | ALH
[8 empty] | Fix obvious level editor problems |  |  | Stop crashing when stopping running the game, fix camera view when not running the game |  | Yes | AJH
Implement range of frame buffer effects that use frame buffer colour attachment |  |  | Create shader source code for inversed colour, grayscale and metallic effects, integrate shader source code into JSONLayer class |  |  | Yes | ALH
[8 empty] | Raycasting |  |  | Make functionality for raycasting for it to be used from Lua Scripts |  | Yes | AJH
Implement frame buffer effect cycling |  |  | Enable frame buffer effects to be toggled during runtime |  |  | Yes | ALH
[8 empty] | Implement additional frame buffer effects |  |  | Create shader source code and integrate into the JSONLayer class, and support toggle capability |  | Yes | ALH
[8 empty] | Implement wireframe mode, applied to frame buffer effects |  |  | Support wireframe mode, showing object primitives used in parallel to frame buffer effects. Integrate into toggle capabilties |  | Yes | ALH
[8 empty] | Implement multi-pass rendering for supporting shadow mapping |  |  | Create shader source code, and refactor JSONLayer class, as well as frame buffer interface classes for supporting multiple render passes |  | No | ALH
Sprint ID | 10 | Period | 2020-06-07 |  | 2020-06-21 |  |  | Sprint ID | 11 | Period | 2020-06-22 | 2020-07-06 |  |  | Sprint ID | 12 | Period | 2020-07-07 | 2020-07-21
Work Item |  |  | Criteria |  |  | Complete? | Developer | Work Item |  |  | Criteria |  | Complete? | Developer | Work Item |  |  | Criteria |  | Complete? | Developer
Link Alfie's raycasting with Lua |  |  | Use Luabridge to link Alfie's functionality with Lua |  |  | Yes | JWM | Define a Prefab class |  |  | Define a Prefab class that will be used to hold the necessary information to create an object during the game's run-time |  | Yes | JWM | Add coliders to prefab/instantiate functionality in Lua |  |  | Prefabs must hold information for colliders and instantiate functions must add them to the object |  | Yes | JWM
Maintain Lua Script help window |  |  | Continue to add to and maintain the Lua Script help window as more functionality is added to the component |  |  | Yes | JWM
[8 empty] | Implement Instantiate functionality |  |  | Create in C++ and subsequently link to Lua scripts, instantiate functions that will create an object in the game from a prefab at run-time |  | Yes | JWM | Add Lua scripts to prefab/instantiate functionality in Lua |  |  | Prefabs must hold filepath to another Lua script and Instanitate functions must add it to the created object |  | Yes | JWM
Define a Prefab class |  |  | Define a Prefab class that will be used to hold the necessary information to create an object during the game's run-time |  |  | No | JWM
[8 empty] | Maintain Lua Script help window |  |  | Continue to add to and maintain the Lua Script help window as more functionality is added to the component |  | Yes | JWM | Maintain Lua Script help window |  |  | Continue to add to and maintain the Lua Script help window as more functionality is added to the component |  | Yes | JWM
Implement Instantiate functionality |  |  | Create in C++ and subsequently link to Lua scripts, instantiate functions that will create an object in the game from a prefab at run-time |  |  | No | JWM
[8 empty] | Update project management document structure |  |  | Partition project management components into separate work spaces and ensure functions used are working correctly |  | Yes | ALH
Define a LuaVector class |  |  | Create a LuaVector class that can be used as a go-between for vectors in C++ and Lua. Get all other Lua function that use vectors to use this |  |  | Yes | JWM
Add vector maths to LuaVector class |  |  | Add vector maths function to LuaVectors. Include dotproduct, angle between, addition, subtraction and magnitude |  |  | Yes | JWM
Define a LuaColour class |  |  | Make a LuaColour class to use as a go-between for colours within C++ and Lua. Get all other Lua functions that use colours to use this |  |  | Yes | JWM
Add Hexadecimal to LuaColour |  |  | Add the ability to define a colour in a LuaColour object from a hexadecimal string |  |  | Yes | JWM
Add default object meshes to Lua |  |  | Add default object mesh filepaths to Lua as read-only variables, so they can be set as the object model. Add them to possible prefabs too |  |  | Yes | JWM
Define RaycastHit class |  |  | Define a RaycastHit class that will be used to store the returned information from a raycast |  |  | Yes | JWM
Raycasting |  |  | Fix problems found linking raycasting with Lua Script |  |  | Yes | AJH
Make the level editor write shaders for objects |  |  | When the game is run, the level editor needs to write shaders specifically for the textures each object has |  |  | Yes | AJH
Update implementation comments |  |  | Ensure all implementation has comments to contextualise functionality |  |  | Yes | ALH
Sprint ID | 13 | Period | 2020-07-22 |  | 2020-08-05 |  |  | Sprint ID | 14 | Period | 2020-08-06 | 2020-08-14
Work Item |  |  | Criteria |  |  | Complete? | Developer | Work Item |  |  | Criteria |  | Complete? | Developer
[8 empty] | Fix issues causing the level editor to go black when running the game too many times/make sure the level editor is as stable as possible |  |  | Stop issues happening when running the game too many times in the level editor, also fix issues happening when changing levels in the level editor |  | Yes | AJH
[8 empty] | Finalise project management deliverables |  |  | Ensure formatting is adhered to for interpretation and charts display information accurately |  | Yes | JWM + AJH + ALH